## Sheet1
NO | TASK | START DATE | DAYS TO COMPITE
1 | Find defination related to society and more detail about project | 2017-12-26 | 7
2 | Find another system related to us and find similar tools from them | 2018-01-01 | 7
3 | Get review from user and to ask them what they want from the | 2018-01-08 | 14
4 | list out main feature of system and what are the requirement | 2018-01-22 | 9
5 | calculate analysis,feasibility study and requirements elicitation | 2018-01-31 | 6
6 | web map and user story board | 2018-02-05 | 7
7 | UML diagram | 2018-02-12 | 7
8 | dividing work between group member | 2018-02-19 | 3
9 | work on wireframe | 2018-02-21 | 10
10 | coding | 2018-03-02 | 23
11 | configuration and debugging | 2018-03-25 | 9
12 | testing | 2018-04-02 | 9
13 | outcome of usability evalution | 2018-04-10 | 3